## Product Backlog
Project Name : ERP
Client: ERP client
Created By : Name of the product owner
Creation Date : dd-mm-yyyy
Approval Date: dd-mm-yyyy
Version : 1.0
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria
ERP_EPIC_001 For a new ERP website to launch.the highest Bussiness value will be when a user is able to buy an item | US001 | Registration | As a First-time visitor to e-commerce website, I want to register my account. So that I can login in to application | New | New user should be able to Register account with valid data
| US002 | Login | As a Registered user , I want to login to the website, so that I can see my account details etc | New | system must validate user credentials and allow login if credentials are correct.
| US003 | Logout | As a Registered user , I want to logout from website, so that no one else can't see my account details etc | New | system must logout after login.
| US004 | User Search Products | As a user I want to be able to search items. So that I can add them to cart and do payment | New | user should be able to search products and add them to cart.

## sprint planning
Project Name : ERP
Client: ERP client
Created By : Name of the scrum master
Creation Date : dd-mm-yyyy
Attendees: scrum team
Version : 1.0
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprint
ERP_EPIC_001 For a new ERP website to launch.the highest Bussiness value will be when a user is able to buy an item | US001 | Registration | As a First-time visitor to e-commerce website, I want to register my account. So that I can login in to application | 8 | 1
| US002 | Login | As a Registered user , I want to login to the website, so that I can see my account details etc | 5 | 1
| US003 | Logout | As a Registered user , I want to logout from website, so that no one else can't see my account details etc | 3 | 1
| US004 | User Search Products | As a user I want to be able to search items. So that I can add them to cart and do payment | 5 | 1

## Tasks
Developer Tasks | QA Tasks
Understanding Requirements | Understanding Requirements
Design | Writing Test Scenarios
Coding | Writing Test Cases
Unit Testing | Test Case Reviews
Integration Testing | Test Data Preparation
Code Review | Test Environment Setup
Bug Fixes | Test Execution
Team Meetings… | Re-Testing Bugs
Any Other | Team Meetings..
Automation
Any Other